## Internal_Detailed_Estimate_Plan
No | WI Name | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Assignee | Estimate (hours) | Build | Process | WI
1 | 222628 As a Content Manager, I want the system to automatically remap and sync IM information whenever it is updated in MSS, so that the item data is always up to date for accurate comparison and exception tracking.
Requirement Analysis and Document (Hours)
|  |  | ENH_222628_Update Documents |  |  |  | LoanPNT | 1
|  |  | ENH_222628_Create UAT |  |  |  | LoanPNT | 1
|  |  | ENH_222628_Verify Requirements |  |  |  | LoanPNT | 1
Implementation (Hours)
Design
|  |  |  | ENH_222628_Review Code/Design |  |  | TienLT | 0
|  |  |  | ENH_222628_How to |  |  | SuNT | 1
|  |  |  | ENH_222628_Load file design |  |  | SuNT | 1
Implement Business Logic
|  |  |  | ENH_222628_Add check point for remap item |  |  | SuNT | 1
|  |  |  | ENH_222628_Enhance process evaluator to recalc item for both new and old po_lines |  |  | SuNT | 4
|  |  |  | ENH_222628_Enhance process evaluator to recalc contract for both new and old po_lines |  |  | SuNT | 3
|  |  |  | ENH_222628_Enhance convert service to revert to orignal value when matched item is removed |  |  | SuNT | 3
|  |  |  | ENH_222628_Benmark perf |  |  | SuNT | 2
|  |  |  | ENH_222628_Add history when item/contract rematch/remove |  |  | SuNT | 3
|  |  |  | ENH_222628_Enhance resolve api to check item out of date |  |  | SuNT | 1
|  |  |  | ENH_222628_Enhance resolution api to check item out of date |  |  | SuNT | 1
|  |  |  | ENH_222628_Expose exception evaluator for api using |  |  | SuNT | 2
Implement GUI
|  |  |  | ENH_222628_PODetailPage - Enhance param useCase - Resolves |  |  | TrungBN | 1
|  |  |  | ENH_222628_PODetailPage - Enhance param useCase - SetUOM |  |  | TrungBN | 1
|  |  |  | ENH_222628_PODetailPage - useCases - handleCallback Resolves + setUOM |  |  | TrungBN | 2
|  |  |  | ENH_222628_PODetailPage - Validation |  |  | TrungBN | 2
Unit Test BE
|  |  |  | ENH_222628_Unit test |  |  | SuNT | 2
|  |  |  | ENH_222628_Manual test |  |  | SuNT | 3
Unit Test FE
|  |  |  | ENH_222628_PODetailPage - Unit test |  |  | TrungBN | 1
Testing (Hours for n Rounds)
Study Requirement(QC)
|  |  |  | ENH_222628_Study Requirement |  |  | SonNT | 1
Update Test Case
|  |  |  | ENH_222628_Logic to trigger the re-mapping Item Master |  |  | SonNT | 2
|  |  |  | ENH_222628_Track Information Changes in Item Master |  |  | SonNT | 2.5
|  |  |  | ENH_222628_Logic to trigger the re-mapping Item CTR |  |  | SonNT | 2
|  |  |  | ENH_222628_Track Information Changes in CTR |  |  | SonNT | 2.5
Execute Test and Regresstion Test
|  |  |  | ENH_222628_Logic to trigger the re-mapping Item IM |  |  | SonNT | 1.75
|  |  |  | ENH_222628_Track Information Changes in Item Master |  |  | SonNT | 2.5
|  |  |  | ENH_222628_Logic to trigger the re-mapping Item CTR |  |  | SonNT | 1.75
|  |  |  | ENH_222628_Track Information Changes in CTR |  |  | SonNT | 2.5
|  |  |  | ENH_222628_Smoke test ITM/CTR |  |  | SonNT | 2
Summary Report
|  |  |  | Test Summary Report Sep 01 |  |  | SonNT | 1
Performance
|  |  |  | ENH_222628_Performance test for mapping ITM/CTR |  |  | SonNT | 1
Review Test Case
|  |  |  | Self- Review test cases |  |  | SonNT | 2.5
|  |  |  | Review test cases |  |  | ThoaHTK | 3